## Bronte
Name | Bronte Mckeown | Project Group (Number) | 3
Week | Date | Activity/Task | Time Spent (minutes) | Other members involved (if applicable) | Completed (y/n) | Notes
1 | 28/07/24 | Idea research | 120 |  | y | Looked into available healthcare APIs
1 | 28/07/24 | Set up Jira, GitHub and Google Drive docs | 180 |  | y | Set up systems for project. Made meeting notes. Added everyone as collaborators.
1 | 28/07/2024 | Team meeting | 90 | Everyone | y | Didn't get through meeting notes as planned but agreed everyone would put forward specific idea by Tuesday to agree on Wednesday.
2 | 29/07/2024 | Idea planning | 60 |  | y | Found dataset and planned idea for weds meeting
2 | 31/07/2024 | Team meeting | 10 | Eva, Wendy, Saorise | y | Agreed on idea and that Saorise would do questions 1-3
2 | 2024-01-08 | Project assignment question 4 work | 20 |  | y
2 | 2024-01-08 | Project assignment and allocation of roles and timeline meeting | 120 | Saoirse, Alazne, Eva | y
3 | 2024-08-08 | Code review of data read in and cleaning | 120 | Saoirse | y
5 | 19/08/2024 | Code review of data exploration | 90 | Saoirse | y
5 | 20/08/2024 | Tidied up data vis and exploration | 90 |  | y
5 | 21/08/2024 | Started machine learning | 90 | Saoirse | y
5 | 22/08/2024 | Added more mark down and added comments, rearranged code | 60 |  | y
5 | 22/08/2024 | Machine learning | 120 | Saoirse | y
5 | 24/08/2024 | Machine learning, went over standardisation, added final comments | 120 | Saoirse | y
5 | 24/08/2024 | Mark down, sanity checking, saving figures | 120 |  | y
5 | 25/08/2024 | Finalising report and code | 480 | Saoirse | y

## Eva
Name |  | Project Group (Number)
Week | Date | Activity/Task | Time Spent (minutes) | Other members involved (if applicable) | Completed (y/n) | Notes
1 | 28/07/2024 | Team meeting | 90 | Everyone | y | Didn't get through meeting notes as planned but agreed everyone would put forward specific idea by Tuesday to agree on Wednesday.
2 | 31/07/2024 | Team meeting | 10 | Eva, Wendy, Saorise, Bronte | y | Agreed on idea and that Saorise would do questions 1-3
2 | 2024-01-08 | Project assignment and allocation of roles and timeline meeting | 120 | Saoirse, Alazne, Eva, Bronte | y
2 | 2024-03-08 | Implementing the Kaggle API into the code and importing the dataset into Jupyter Notebook. | 90 | Eva | y | Forgot to put in my notebook the requirements to use kaggle.
2 | 2024-03-08 | Perfomed data cleansing using the agreed-upon columns of the Kaggle Dataset, focusing on identifying missing data. | 130 | Eva | y | Didn't find any missing data, neither in columns nor rows.
2 | 2024-04-08 | Meeting to review our progress and evaluate our coding efforts. | 60 | Eva and Alazne | y | We agreed that we needed to look for outliers in our data.
5 | 19/08/2024 | Started writing the Introduction section of the project. | 90 | Eva | y
5 | 20/08/2024 | Wrote a section detailing our data cleaning process | 35 | Eva | y
5 | 20/08/2024 | Meeting to review our progress | 30 | Eva and Alazne | y
5 | 23/08/2024 | Added our sections to the group project and edited | 20 | Eva

## Wendy
Name |  | Project Group (Number)
Week | Date | Activity/Task | Time Spent (minutes) | Other members involved (if applicable) | Completed (y/n) | Notes
week 3 | 2024-12-08 | Meeting Exploratory data analysis | 135 | Yasmeen | Y
week 3 | 13/08/2024 | Worked on Data analysis and Heatmaps | 120 |  | Y
week 3 | 14/08/2024 | Worked on Data analysis and Heatmaps | 120 |  | Y
week 3 | 15/08/2024 | Meeting Evaluate most suitable statistical approach | 90 | Yasmeen | Y
week3 | 16/08/2024 | Worked on Data Visualisation | 30 |  | Y
week 5 |  | Report write up

## Yasmeen
Name | Yasmeen Nazzal | Project Group (Number) | 3
Week | Date | Activity/Task | Time Spent (minutes) | Other members involved (if applicable) | Completed (y/n) | Notes
1 | 28/07/2024 | Research idea | 120 |  | Y | Idea shared with team in Slack channel 28/07/2024
1 | 28/07/2024 | Team meeting | 90 | Everyone | Y
2 | HOLIDAY
3 | 2024-12-08 | EDA Meeting | 135 | Wendy | Y
3 | 13/08/2024 | EDA & Viz | 300 |  | Y
3 | 14/08/2024 | EDA & Viz | 300 |  | Y
3 | 15/08/2024 | EDA Meeting | 90 | Wendy | Y
3 | 15/08/2024 | EDA & Viz | 300
3 | 15/08/2024 | Team Meeting | 40 | Wendy / Eva | Y
Links |  |  | SWOT Analysis
Google drive contains all docs we want to collaborate on: |  |  | Strengths
https://drive.google.com/drive/u/0/folders/15m42KSadUWLinzhz09H_wk92N-xmS80b |  |  | 1. I studied some Machine Learning at university so I feel I could lead on this aspect of our project!
2. I have multiple years of Tableau data viz work experience if we ever need any dashboards created.
This is the GitHub which so far just has CFG docs in: |  |  | 3. I have decent presentation skills
https://github.com/Bronte-Mckeown/ds-2-group-3 |  |  | 4. I'm not too bad at coding but still a beginner.
Weaknesses
This is the Jira timeline: |  |  | 1. Report writing is no my best area unfortunately!!
https://ds-2-group-3.atlassian.net/jira/software/projects/GP/boards/2/timeline |  |  | 2. API handling and SQL skills could be stronger.
Opportunities
This is the Jira board (for small to-dos): |  |  | 1. Improve coding skills (SQL and Python)
https://ds-2-group-3.atlassian.net/jira/software/projects/GP/boards/2 |  |  | 2. Definitely API practice too
Threats
This is the link for calendars: |  |  | 1. Out on holiday 2nd week of the project
https://ds-2-group-3.atlassian.net/wiki/spaces/THFMV/calendars |  |  | 2. Working full time and travelling around
Project Idea
Project: | Predicting the likelihood of diabetes
Dataset: | https://www.kaggle.com/datasets/iammustafatz/diabetes-prediction-dataset
Columns: | Gender, Age, Hypertension, Heart Disease, Smoking History, BMI, HbA1c, Blood Glucose Levels, Diabetes flag
Question 1 - What is your project question(s) and the problem it tackles? | [5 empty] | ▪ You will be marked on how realistic the problem is given the project timeline, as well as the fit with the subjects covered throughout the Data Specialisation and your personal, common interests in the topic.
Can we predict the likelihood of diabetes in individuals based on demographic and health-related features using machine learning models?
Diabetes is a chronic disease, which if not managed properly, can lead to serious health complications. Machine learning models can help make early predictions,
which can lead to timely intervention, better management and improved health outcomes for patient. The project aims to use the "Diabeted Prediction Dataset" to identify
individuals at risk of developing diabetes from various demographic and health markers.
Question 2 - Explain your target audience. Who could be interested in reading your final report and for whom will your project be useful? Assess the level of expertise in relation to data science of your audience (for example, how technical should your report/presentation be?). | [5 empty] | ▪ You will be marked on correctly identifying your audience and the technical level of your presentation and report.
Patients or individuals who are interested in understanding their health risks and advocating for preventive care.
Doctors and nurses who can use predictive insights to identify patients at risk of diabetes early.
The presentation can be moderately technical but not overly complicated. It should be informative and insightful to both patients and healthcare providers.
Question 3 - What data sources will you need to answer your project question(s)? | [5 empty] | Describe any potential issues you can have with the datasets and how will you overcome this: For example, will the data you find only cover particular geographical areas? Will you need to combine multiple datasets to overcome this?
The dataset might be biased towards certain populations or regions.
Missing or inaccurate data can affect model performance. We can address this with data cleaning techniques such as missing-value handling etc.
Insights & Findings
Data Cleaning & Preprocessing
1. Convert data types if needed.
2. Identify missing values and how to deal with them.
3. Normalise and scale data (data standardization)
Exploratory Data Analysis
1. Descriptive Statistics - Understand the central tendency of each feature/variable in our dataset through the mean and median.
2. Distribution Analysis - Visualise the distribution of variables to identify skewness and potential outliers through histograms for example.
3. Correlation Analysis - To identify correlations between features/variables.
Model Building
1. Use scikit-learn library to split data into a training set and testing set.
2. Algorithm Testing - compare different machine learning algorithms such as logistic regression, decision trees, random forest etc.
3. Use performance metrics to evaluate the different machine learning models to determine which model works best for predicting diabetes.
Reporting & Visualisation
1. Visualise analysis charts using matplotlib/seaborn.
2. Possible to visualise a dashboard using Tableau or PowerBI.
3. Documentation of outcomes while tailoring the report to our target audience (ensure accessibility for non-technical audience).

## Saoirse
Name |  | Project Group (Number)
Week | Date | Activity/Task | Time Spent (minutes) | Other members involved | Completed (y/n) | Notes
1 | 28/07/24 | Idea research | 120 |  | y | Researched Various API'S on kaggle
1 | 28/07/2024 | Team meeting | 90 | Everyone | y | Agreed to finalise our ideas before following meeting
2 | 29/07/2024 | Idea planning | 30 |  | y | Found a dataset
2 | 31/07/2024 | Team meeting | 10 | Bronte, Eva and Wendy | y | Decided to go with Alzheimers data
3 | 31/07/2025 | Answerig questions 1-3 | 60 |  | y | Summarised our idea answering relevant sections
2 | 2024-01-08 | Project assignment and allocation of roles and timeline meeting |  | Bronte, Alazne and Eva | y
3 | 2024-08-08 | Code review of data read in and cleaning | 100 | Bronte | y
5 | 19/08/2024 | Code review of data exploration | 90 | Bronte | y
5 | 21/08/2024 | Started machine learning | 90 | Bronte | y
5 | 22/08/2024 | Machine learning | 120 | Bronte | y
5 | 23/08/2024 | Code refactoring | 120 |  | y | We noticed a data leak so modified the standardisation procedures
5 | 24/08/2025 | Machine learning, added final comments etc | 120 | Bronte | y
5 | 25/08/2024 | Finalising report and code | 480 | Bronte | y

## Alazne
Name |  | Project Group (Number)
Week | Date | Activity/Task | Time Spent (minutes) | Other members involved (if applicable) | Completed (y/n) | Notes
1 | 28/07/24 | Idea research | 120 |  | y | Research different API ideas with the team
1 | 28/07/24 | Team meeting | 90 | Everyone | y | Agreed to select a dataset for the next team meeting
2 | 2024-01-08 | Project assignment and allocation of roles and timeline meeting | 120 | Bronte, Saoirse and Eva | y
2 | 2024-02-08 | Fetching the Kaggle API and initial dataset reaeding into Jupyter Notebook | 120 |  | y
2 | 2024-03-08 | Dataset data cleaning in Jupyter Notebook | 120 |  | y
2 | 2024-04-08 | Meeting to review our progress and evaluate our coding efforts. | 60 | Eva | y | Agreed that needed to look for outliers in our data and unify all both works in the same notebook.
3 | 2024-06-08 | Unify the code of data cleaning part, complete the notebook with comments and share with the team in slack and Github new branch for collaboration | 120 |  | y | Share the first part of the project with the team
5 | 19/08/2024 | Report part writings | 45 |  | y
5 | 20/08/2024 | Meeting with Eva to review report part | 30 | Eva | y
5 | 20/08/2024 | Meeting with Yasmeen to review report part | 30 | Yasmeen | y
5 | 22/08/2024 | Teem meeting | 20 | Yasmeen | y | Team meeting to check our progress of the project